## SDP
WORK BREAKDOWN STRUCTURE
Project Manager: |  | AMTOUT Oualid |  |  | Project |  | Team Size: 1 (AMTOUT Oualid ) : Internal 1 : External 0
Context |  |  |  |  | Design and Development of an AI-Powered Recruitment Platform Built on SAP BTP using ABAP RAP |  | Objectives
As part of modernizing Human Capital Management (HCM) processes within the SAP ecosystem and adopting Clean Core principles, digitalizing and automating the recruitment lifecycle represent a major strategic lever. Addressing the ergonomic limitations of classic SAP GUI, the cognitive overload of manual applicant screening, and the need to decouple modern user interfaces from the ERP core without compromising its integrity, this project develops an intelligent talent acquisition solution built side by side on SAP BTP (ABAP Environment) with the ABAP RAP framework and an AI microservice. | [6 empty] | 1. Model HR structures and job openings on SAP HANA using ABAP CDS and secure transactional logic (BDEF). 2. Expose standardized OData V4 APIs for seamless, decoupled integration with external applications. 3. Develop a modern web portal (React/Vite) for candidates and SAP Fiori Elements apps for HR. 4. Integrate an AI microservice (FastAPI, GPT-4o-mini) for automated resume parsing and scoring. 5. Master the SAP BTP / ABAP RAP stack through SAP Learning courses and formalize project management (Charter, SDP, internship report).
Goal
Replace manual, siloed recruitment workflows with an intuitive, decoupled web platform enabling candidates to apply online and HR teams to automate screening with AI-driven resume scoring and to onboard selected hires into the HCM organizational structure on SAP BTP, ensuring responsiveness, traceability, and Clean Core compliance.
Work Package 1 |  |  | Work Package 2 |  | Work Package 3 |  | Work Package 4 |  | Work Package 5
Project Management and Training |  |  | Requirements & Specifications Analysis |  | UI/UX Prototyping |  | Backend & Frontend Development |  | Testing & Deployment
1.1 | Draft the Project Charter |  | 2.1 | Analyze legacy system limitations and issues | 3.1 | User Journey Mapping (Applicant Experience & HR Administrative Workflow) | 4.1 | Cloud development setup & technology stack selection | 5.1 | Unit & integration testing (ABAP & API contract validation)
1.2 | Draft the Team Charter |  | 2.2 | SAP HCM Recruitment & Personnel Administration Workflow Analysis | 3.2 | User experience exploration with Excalidraw sketches | 4.2 | Generating database tables (transparent active & draft tables) | 5.2 | Testing the pipeline (recruitment pipeline & candidate flow)
1.3 | Develop the Project Plan (SDP) |  | 2.3 | Functional & Non-Functional Requirements Specification | 3.3 | Low-Fidelity Wireframing for Public Candidate Job Portal | 4.3 | Interface CDS View Entities Modeling | 5.3 | Testing the adding employee process (onboarding & conversion)
1.4 | Conduct Project Monitoring & Tracking |  | 2.4 | Stakeholder Use Case Modeling (Candidate Portal & HR Recruiter) | 3.4 | Interactive Design for Job Application & Digital Onboarding Forms | 4.4 | Consumption CDS Projection Views Modeling | 5.4 | Testing edge cases (error handling, invalid formats, boundary values)
1.5 | Get the free trial account (SAP BTP Setup) |  | 2.5 | Comparative Study & Selection of NLP Model for Resume Semantic Scoring | 3.5 | High-Fidelity HR Cockpit Mockups Aligned with SAP Fiori Guidelines | 4.5 | Behavior Definitions (BDEF) implementation: determinations, validations & actions | 5.5 | End-to-end testing (Front-end <-> AI Microservice <-> SAP RAP)
1.6 | Complete SAP course: Exploring SAP Business Technology Platform (BTP100) |  | 2.6 | Design Conceptual Data Model (CDM) for the target database | 3.6 | Visual style definition (colors, typography, components) | 4.6 | Structuring Business Objects (BO composition trees & aggregates) | 5.6 | Deployment on the SAP BTP trial environment & handover
1.7 | Complete SAP course: Building Transactional Apps with the ABAP RESTful Application Programming Model (S4D437) |  |  |  | 3.7 | Design System Definition & Reusable UI Component Library Formulation | 4.7 | Business Service Definitions & Service Bindings (OData V4)
1.8 | Complete SAP course: Learning Basic ABAP Programming (S4D400) | [5 empty] | 4.8 | Build the modern front-end web portal (React / Vite / Tailwind)
1.9 | Draft the Project Report | [5 empty] | 4.9 | AI microservice integration for CV parsing & scoring (FastAPI)
1.10 | Draft the Project Closure Report
Deliverables: | Project Charter, Team Charter, Project Plan (SDP), Active SAP BTP Account, SAP Learning course completion badges, Project Report, Project Closure Report. |  | Deliverable(s): | Legacy System & Limitations Analysis, Requirements Specifications (Functional & Non-Functional), Use Case Diagrams, NLP Model Comparative Study, Conceptual Data Model (CDM). | Deliverable(s): | User Journey Maps, Excalidraw Mockups, Public Portal Low-Fidelity Wireframes, Interactive Application & Onboarding Forms, Fiori High-Fidelity Mockups, Graphic Style Guide & Design System. | Deliverable(s): | Configured BTP Cloud Environment, Database Schema & Tables, CDS Views & Projections, Behavior Definitions (BDEF) & Business Objects, Exposed OData V4 Services, Modern Web Portal (Frontend), Operational AI Microservice. | Deliverable(s): | Unit & Integration Test Reports, Recruitment Pipeline & Onboarding Test Suite, Edge Cases Validation Report, End-to-End Test Scenario & SAP BTP Deployment Validation.

## Fiche de Lot 1
FICHE DE LOT |  |  |  |  | CHARTE DES RESPONSABILITÉS | [5 empty] | ÉCHÉANCIER
NOM DU LOT: | #ERROR! | RESPONSABLE DU LOT: |  | #REF! | [6 empty] | Durée | Date début planifiée: | [5 empty] | Date fin planifiée:
Livrable(s): | #ERROR!
Noms des Ressources
[12 empty] | S1 : 15/06 | S2 : 22/06 | S3 : 29/06 | S4 : 06/07 | S5 : 13/07 | S6 : 20/07 | S7 : 27/07 | S8 : 03/08 | S9 : 10/08
Tâches | Description de la tâche | Date debut | Date fin | Tâche précedente | A | B | C | D | E | F
2,1
2
3
4
5
6
7
2,1
9
10
11
12
13

## Fiche de Lot 2
FICHE DE LOT |  |  |  |  | CHARTE DES RESPONSABILITÉS | [5 empty] | ÉCHÉANCIER
NOM DU LOT: |  | RESPONSABLE DU LOT: | [8 empty] | Durée | Date début planifiée: | [5 empty] | Date fin planifiée:
Livrable(s):
Noms des Ressources
[12 empty] | S1 : 15/06 | S2 : 22/06 | S3 : 29/06 | S4 : 06/07 | S5 : 13/07 | S6 : 20/07 | S7 : 27/07 | S8 : 03/08 | S9 : 10/08
Tâches | Description de la tâche | Date debut | Date fin | Tâche précedente | A | B | C | D | E | F
2,1
2
3
4
5
6
7
2,1
9
10
11
12
13

## Fiche de lot 3
FICHE DE LOT |  |  |  |  | CHARTE DES RESPONSABILITÉS | [5 empty] | ÉCHÉANCIER
NOM DU LOT: |  | RESPONSABLE DU LOT: | [8 empty] | Durée | Date début planifiée: | [5 empty] | Date fin planifiée:
Livrable(s):
Noms des Ressources
[12 empty] | S1 : 15/06 | S2 : 22/06 | S3 : 29/06 | S4 : 06/07 | S5 : 13/07 | S6 : 20/07 | S7 : 27/07 | S8 : 03/08 | S9 : 10/08
Tâches | Description de la tâche | Date debut | Date fin | Tâche précedente | A | B | C | D | E | F
2,1
2
3
4
5
6
7
2,1
9
10
11
12
13